MICHELMERSH & TIMSBURY
MINUTES OF
NEIGHBOURHOOD DEVELOPMENT PLAN
STEERING GROUP MEETING No. 11
HELD AT JUBILEE HALL, NEW ROAD
ON
MONDAY 09 MAY 2022 AT 1930hrs

PRESENT:		Bob Davis (RD)
		Sarah Bone (Sarah B)
			Steve Langford (SL)	
			Deborah Sacree (DS)		
			Melanie Liddell (ML)
			Geoff Taylor (GAT)
	
APOLOGIES:	Sharon Burns (Sharon B)
	Ed Pratt (EP)
		Roger Savage (RS)
		Ray Sheehan (RS)
		Marcus Evans (ME)
	Jane Chambers (JC)
		Sarah Medley (SM)
		
DISTRIBUTION: PRESENT + APOLOGIES

	ITEM
	
	ACTION

	1.00
	APOLOGIES FOR ABSENCE
	

	1.01
	As listed above.
	Note

	
	
	

	2.00
	MINUTES OF LAST MEETING
	

	2.01
	Received by all and agreed as a true record.
	Note

	
	
	

	3.00
	MATTERS ARISING (Not on this Agenda)
	

	3.01
	GAT has circulated a draft “contents” list for the public exhibition. 
	Note

	
	
	

	3.02
	RD has chased Sharon Brentnall for her report. Three drafts have been received, commented upon by RD and returned. RD will chase for a final version. It was agreed this was to be labelled “Commercial-in-Confidence” until released by the Parish Council and this Steering Group when it would be placed in the public domain by inclusion on the M&T website. The target for this is end May 2022.
	RD

	
	
	

	3.03
	The Housing Needs Assessment written by Aecom has shown that some 90 “Affordable” dwellings are required in the Parish. This has to be wrong when compared to the c900 total dwellings required in the whole of Test Valley. Sharon Brentnall has commented on this and other items to Aecom and a revised version is in progress. RD will chase.
	RD

	
	
	

	4.00
	UPDATE – Survey Matters
	

	4.01
	There has been no progress on the Business Consultation save that RD has drafted a proposed set of questions and a hard copy was circulated at the meeting. The Steering Group reviewed the proposed questions and considered this was a very reasonable set. RD will talk to Ed Pratt and ML regarding setting up a “Google Survey” or similar and it was agreed to try to get this out to businesses registered in the Parish by the end of May 2022.
	RD
EP
ML


	
	
	

	4.02
	In respect of the Young Persons Consultation there had also been little progress due to current pressures of work being experienced by Steering Group Members. RD volunteered to contact Roger Savage who had offered to lead on this aspect to see what can be done to expedite matters. Discussion too place on the likely volume of questions and it was agreed that it was probably a maximum of 10 questions. Key questions would relate to what facilities the young would like to see now and what would induce them to stay, if not in the Parish, then certainly local. The questionnaire would be placed on the M&T Facebook page when ready.
	RD

	
	
	

	4.03
	The content of the Public Consultation/Exhibition in respect of the surveys was discussed. It was agreed that a summary of each of the survey analyses should be prepared and included. Sarah B agreed to look further at the work she has already done in respect of the Domestic Consultation already carried out. Sarah B will try to summarise the findings in a circa 4 or 5 PowerPoint slide presentation onto which the summaries of Business and Young Persons consultations can be grafted in due course.
	Sarah B

	
	
	

	5.00
	TIMESCALES  
	

	5.01
	It was agreed that we have slipped on our declared programme for consultation and that it was key to focus on the 2 consultations to be undertaken before we can move forward with meaningful drafting of the NDP. An aspiration of a Public Exhibition in the second half of September 2022 needs to be maintained.
	All

	
	
	

	5.02
	The concept of 2 Public Meetings, one on a weekday evening and one on a Saturday morning was maintained as a working assumption.
	Note

	
	
	

	6.00
	NEXT STEPS
	

	6.01
	Several Members have offered photographs of spaces and views which they believe are significant/important.
	Note


	
	
	

	7.00
	AOB
	

	7.01
	DS reaffirmed that consultation with the younger members of the community was important. RD would speak to both RS and EP who have direct links with younger folk.
	RD/RS/EP

	
	
	

	8.00
	NEXT MEETING
	

	8.01
	Monday 13 June 2022 at 1930hrs at Jubilee Hall.
	Note

	
	
	

	8.02
	Meeting ended at 2030hrs.
	Note
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